## <Year 1>
| <Team Member 1> | <Team Member 2> | <Team Member 3> | <Team Member 4> | <Team Member 5>
Sprint 1 | 26 | 15 | 32 | 43 | 38 | <-- Copy from last year. If this is your first year, just tally up the total story points or hours completed at the end of the sprint
Sprint 2 | 43 | 35 | 22 | 40 | 39 | <-- Copy from last year. If this is your first year, just tally up the total story points or hours completed at the end of the sprint
Sprint 3 | 34.5 | 25 | 27 | 41.5 | 38.5
Sprint 4 | 38.75 | 30 | 24.5 | 40.75 | 38.75 | Formula: Sprint c = (Sprint a + Sprint b)/2
Sprint 5 | 36.625 | 27.5 | 25.75 | 41.125 | 38.625 | In other workds: The upcoming sprint = (two sprints before total + one sprint before total)/2
Sprint 6 | 37.6875 | 28.75 | 25.125 | 40.9375 | 38.6875 | Note: Color coding is for department such as frontend, backend, QA, etc. Below is an example color coding with key. Customize how you see fit.
Sprint 7 | 37.1562 | 28.125 | 25.4375 | 41.0312 | 38.6562
Sprint 8 | 37.4219 | 28.4375 | 25.2812 | 40.9844 | 38.6719 | Key:
Sprint 9 | 37.2891 | 28.2812 | 25.3594 | 41.0078 | 38.6641 |  | Frontend
Sprint 10 | 37.3555 | 28.3594 | 25.3203 | 40.9961 | 38.668 |  | Backend
Sprint 11 | 37.3223 | 28.3203 | 25.3398 | 41.002 | 38.666 |  | QA
Sprint 12 | 37.3389 | 28.3398 | 25.3301 | 40.999 | 38.667
Sprint 13 | 37.3306 | 28.3301 | 25.335 | 41.0005 | 38.6665
Sprint 14 | 37.3347 | 28.335 | 25.3325 | 40.9998 | 38.6667
Sprint 15 | 37.3326 | 28.3325 | 25.3337 | 41.0001 | 38.6666
Sprint 16 | 37.3337 | 28.3337 | 25.3331 | 40.9999 | 38.6667
Sprint 17 | 37.3332 | 28.3331 | 25.3334 | 41 | 38.6667
Sprint 18 | 37.3334 | 28.3334 | 25.3333 | 41 | 38.6667
Sprint 19 | 37.3333 | 28.3333 | 25.3334 | 41 | 38.6667
Sprint 20 | 37.3334 | 28.3334 | 25.3333 | 41 | 38.6667
Sprint 21 | 37.3333 | 28.3333 | 25.3333 | 41 | 38.6667
Sprint 22 | 37.3333 | 28.3333 | 25.3333 | 41 | 38.6667
Sprint 23 | 37.3333 | 28.3333 | 25.3333 | 41 | 38.6667
Sprint 24 | 37.3333 | 28.3333 | 25.3333 | 41 | 38.6667
Sprint 25 | 37.3333 | 28.3333 | 25.3333 | 41 | 38.6667
Sprint 26 | 37.3333 | 28.3333 | 25.3333 | 41 | 38.6667